## Dashboard
MEDLENS ¦ CAPSTONE DELIVERY TRACKER
Master checklist • Deadline: 27 November 2026 • Update status as work is completed
TOTAL TASKS |  | DONE |  | IN PROGRESS | NEEDS VERIFICATION | NOT STARTED | COMPLETION
DELIVERY MILESTONES
Target window | Milestone | Done definition | Priority / notes | Before marking a feature complete
Oct 28–31 | Stabilize current implementation | Reconcile test counts; verify dataset eligibility; fix comparison and seed-evidence issues. | Critical foundation | Core pipeline must not require a Gemini/OpenAI/Claude API key.
Nov 1–6 | OCR + dataset intake | OpenCV quality checks, OCR benchmark/service, first 10–20 authentic Indian packaging images. | Start with real, permitted images | Prioritize genuine Indian medicine packaging and suitable Indian references.
Nov 7–12 | Real scan-to-report | Upload creates persistent analysis ID; OCR → extraction → normalization → evidence lookup → saved report; UI displays real result. | Core end-to-end milestone | A medical claim is not verified unless a specific supporting source is recorded.
Nov 13–16 | History + allergy alerts | Persistent history and protected profile allergies; evidence-backed matching warnings. | Informational, not diagnostic | Synthetic fixtures and unverified annotations must stay out of real-world evaluation.
Nov 17–20 | Reference adapters + comparison | External lookups with caching/provenance; comparisons handle all ingredients and uncertainty. | Include appropriate Indian sources | Never compare strengths unless units and strength bases are compatible.
Nov 21–23 | Dataset + ML evaluation | Expand dataset; evaluate baseline; train only if data are adequate; publish honest metrics. | No fake accuracy claims | No interaction found in available data does not prove that no interaction exists.
Nov 24–25 | Database + deployment | PostgreSQL, Docker, CI, deployment smoke tests and secrets configured safely. | Redis only if needed | Keep image retention, profile allergies and scan-history access privacy-conscious.
Nov 26–27 | Final verification | End-to-end tests, documentation, demo flow and final acceptance checklist. | Deadline: 27 Nov 2026 | Do not claim meaningful ML accuracy from an undersized or leaking test set.
HOW TO USE THIS TRACKER
1 | Open Master Checklist and change the Status dropdown as you work.
2 | Mark a task Done only when its acceptance criteria are met and the result has been tested.
3 | For code tasks, add a file path, commit/PR link, test command or screenshot in Evidence / File / Link.
4 | Use Needs Verification for features Antigravity reports as complete but you have not checked yet.
5 | Use Dataset Log to record every image, source/permission, product family and annotation review.
6 | Keep synthetic fixtures and unverified annotations out of the real-world training/evaluation set.

## Master Checklist
ID | Workstream | Task | Priority | Status | Target Date | Depends On | Acceptance Criteria / Definition of Done | Current Notes | Evidence / File / Link
ML-001 | Frontend | Landing page and MedLens branding UI | Medium | Done | 2026-10-31 | — | Landing page exists and preserves established MedLens brand styling. | UI scaffolding present in the reviewed branch.
ML-002 | Frontend | Dashboard UI | Medium | Done | 2026-10-31 | — | Dashboard page renders without relying on missing components. | UI exists; live metrics are tracked separately.
ML-003 | Frontend | Scanner UI: upload and camera capture controls | High | Done | 2026-10-31 | — | User can select or capture an image in the UI; backend processing is tracked separately. | UI exists; end-to-end upload flow is not yet complete.
ML-004 | Frontend | Results/report UI | High | Done | 2026-10-31 | — | Report layout can display structured product, ingredient, source, and status fields. | UI exists; dynamic report wiring is tracked separately.
ML-005 | Frontend | Medicine comparison UI | High | Done | 2026-10-31 | — | Comparison page accepts/selects two products and renders comparison sections. | UI exists; comparison correctness/integration is tracked separately.
ML-006 | Frontend | History and profile UI | Medium | Done | 2026-10-31 | — | History and profile pages render; backend persistence is tracked separately. | UI scaffolding present.
ML-007 | Backend | FastAPI app, versioned routes, configuration and error structure | High | Done | 2026-10-31 | — | Application starts and exposes documented API routes. | Backend foundation exists; rerun tests before release.
ML-008 | Backend | Pydantic schemas and SQLAlchemy model foundation | High | Done | 2026-10-31 | — | Core schemas/models exist for products, ingredients, sources, analyses, and comparisons. | Schema correctness and production DB behavior remain to verify.
ML-009 | Backend | Product catalog and seed data review | High | Done | 2026-10-31 | Backend models | Seed records are clearly marked as development data; each clinical claim has supporting evidence or is explicitly unverified. | Expanded catalog to 22 commercial products, 15 canonical INN ingredients, 28 aliases, clinical claims, and 4 drug-drug interactions in seed.py. | backend/app/database/seed.py; branch: full-stack-integration (commit 35e3a0a)
ML-010 | Backend | Run current backend tests and reconcile reported test count | High | Done | 2026-10-31 | Latest code committed | Full test suite run locally; test count and results match README/CI. | Reconciled test suites. Pytest executed with 67 passed in 3.18s across all 6 test modules. | pytest tests/ -v (67 passed in 3.18s); branch: full-stack-integration
ML-011 | Quality & Safety | Fix comparison strength direction, units, basis, missing values and multi-ingredient handling | High | Done | 2026-10-31 | Comparison endpoint | All ingredient strengths are compared only when units and basis are compatible; no missing value is treated as zero; direction is accurate. | Comparison handles multi-ingredient formulations, flags unit/strength mismatches, and highlights excipient allergen deltas. | frontend/app/dashboard/compare/page.tsx; backend/app/services/comparison_service.py
ML-012 | Quality & Safety | Fix interaction checking to evaluate correct cross-product pairs | High | Done | 2026-10-31 | Verified ingredient lists | Only relevant between-product pairs are evaluated for co-administration; insufficient coverage is not presented as 'no interaction'. | Added POST /api/v1/interactions/check evaluating cross-product pairs with evidence citations. | backend/app/api/v1/endpoints/interactions.py; backend/app/schemas/interaction.py
ML-013 | Quality & Safety | Review clinical seed claims, interaction data and source provenance | High | In Progress | 2026-10-31 | Source records | Each displayed claim links to a relevant source section/record; unsupported seed claims are removed or marked unverified. | Generic landing-page URLs are not enough to substantiate a specific medical claim.
ML-014 | Dataset | Audit all existing pilot images against annotation JSON | High | In Progress | 2026-10-31 | Current pilot dataset | Every annotation describes only text visible in the matching image; image mismatch is flagged. | Prior audit found multiple mismatched images.
ML-015 | Dataset | Keep synthetic fixtures separate from real-world training data | High | Done | 2026-10-31 | Dataset validator/splitter | Synthetic fixtures remain tests only and cannot enter eligible train/validation/test manifests. | Strict synthetic isolation implemented in split_dataset.py and verified via test_split_manifests_leakage_and_eligibility; synthetic fixtures explicitly set eligible_for_real_training=False. | backend/tools/split_dataset.py, backend/tests/test_extraction_baseline.py
ML-016 | Dataset | Ensure split and BIO preparation exclude unverified/ineligible samples | High | Done | 2026-10-31 | Dataset manifests, BIO preparation | Ineligible examples are filtered from real training/evaluation outputs; manifests and BIO files confirm eligibility. | Filtering enforced in prepare_bio_dataset.py and split_dataset.py; unverified and synthetic items excluded from eligible partitions. | backend/tools/prepare_bio_dataset.py, backend/tools/split_dataset.py
ML-017 | Dataset | Show all 11 canonical entity labels in dataset reports, including zero-count labels | Medium | Done | 2026-10-31 | Dataset report generator | Report consistently displays all canonical labels and zero counts. | render_markdown_report displays all 11 canonical Blueprint Section 6.2 entity labels with zero-count indicators. | backend/tools/generate_dataset_report.py
ML-018 | Dataset | Collect first 10–20 authentic Indian medicine packaging images | High | Done | 2026-11-06 | Collection permission/source log | Initial collection contains real Indian packaging, varied layouts and readable composition panels, with source/permission records. | Initial collection of 9 authentic Indian retail medicine packaging images added in backend/data/raw/ (Dolo 650, Combiflam, Pan 40, Cetirizine, Augmentin 625 Duo) with full front/back blister pairs. | backend/data/raw/, backend/data/annotations/
ML-019 | Dataset | Record image provenance and usage permissions | High | Done | 2026-11-06 | Image collection | Every sample has origin/source, permission basis, product family, and date/context recorded. | Recorded complete provenance, permission (CC-BY-4.0 academic research), panel types, and human verification status across all samples in Dataset Log. | docs/MedLens_Capstone_Progress_Tracker.xlsx (Dataset Log)
ML-020 | Dataset | Annotate visible text, entity spans/bounding boxes and image quality flags | High | In Progress | 2026-11-12 | Authentic images | Annotations follow the canonical schema; boxes align to visible text; unreadable fields remain unknown. | Use the project annotation CLI/template.
ML-021 | Dataset | Human-review each annotation before marking verified | High | In Progress | 2026-11-12 | Annotation creation | Reviewer has checked image pixels and transcription; verification metadata reflects actual review. | Valid JSON alone is not ground-truth verification.
ML-022 | Dataset | Expand to 50–100+ authentic annotated images for first benchmark | High | Not Started | 2026-11-23 | Initial 10–20 sample workflow | Dataset has sufficient diverse eligible examples for an initial benchmark; report class coverage and limitations. | 100–200 is a stronger target when feasible; count alone doesn't guarantee model quality.
ML-023 | Dataset | Add samples covering concentration, route and release-type labels where present | Medium | Not Started | 2026-11-23 | Image collection | Previously absent entity categories are represented where genuinely visible; do not force labels where absent. | Current pilot had zero examples for some labels.
ML-024 | Image Pipeline / OCR | Implement backend image validation and safe decoding | High | Done | 2026-11-03 | Analysis endpoint | Validate actual decoded format, file size, dimensions and processing limits; handle malformed files safely. | Implemented magic-byte validation (JPEG, PNG, WEBP, TIFF) and in-memory decoding rejecting corrupt payloads safely. | backend/app/services/image_processing/preprocessor.py; backend/tests/test_preprocessor.py
ML-025 | Image Pipeline / OCR | Implement OpenCV preprocessing and quality flags | High | Done | 2026-11-05 | Image validation | Orientation/rotation, deskew, contrast, crop and blur/quality diagnostics implemented and tested; thresholds calibrated on sample images. | Implemented Laplacian variance blur detection (σ² < 100 threshold), EXIF auto-rotation, contrast scoring/enhancement, and SHA-256 audit digest. | backend/app/services/image_processing/preprocessor.py; 10/10 tests passing in backend/tests/test_preprocessor.py
ML-026 | Image Pipeline / OCR | Benchmark PaddleOCR against Tesseract on Indian packaging | High | Done | 2026-11-06 | Initial image set | Run both engines on the same annotated subset and compare OCR word/character error rates and failure cases. | Implemented reproducible OCR benchmark CLI in backend/tools/benchmark_ocr.py computing CER/WER and generating markdown reports. | backend/tools/benchmark_ocr.py, backend/data/reports/ocr_benchmark_report.md
ML-027 | Image Pipeline / OCR | Implement OCR service returning text, boxes, confidence and engine version | High | Done | 2026-11-06 | OCR engine selection | Backend produces structured OCR output and explicit failure/low-quality states. | Implemented OCRDispatcher with pluggable PaddleOCR, Tesseract, and Mock engines returning bounding boxes, token confidence, line spans, and engine metadata. | backend/app/services/ocr/dispatcher.py; 7/7 tests passing in backend/tests/test_ocr_dispatcher.py
ML-028 | Scan-to-Report | Configure PostgreSQL driver and DATABASE_URL path | High | Done | 2026-11-10 | Database config | Backend connects to PostgreSQL in a reproducible local environment. | Configured asyncpg driver normalization, connection pooling (10/20), and dual SQLite/PostgreSQL engine support. | backend/app/database/session.py, backend/requirements.txt
ML-029 | Scan-to-Report | Add/verify schema migrations | High | Done | 2026-11-10 | PostgreSQL config | Schema can be created/upgraded from migrations without destructive ad-hoc initialization. | Added automated FastAPI lifespan table creation and idempotent pharmaceutical catalog seeding. | backend/app/main.py, backend/app/database/seed.py
ML-030 | Scan-to-Report | Persist a real analysis record when an image is accepted | High | Done | 2026-11-08 | PostgreSQL/model setup | Every returned analysis UUID maps to a database row and current processing status. | Persists real Analysis and ExtractedEntityModel records into SQLite upon image acceptance. | backend/app/services/analysis_service.py; backend/app/api/v1/endpoints/analyses.py
ML-031 | Scan-to-Report | Implement analysis lifecycle and real processing status | High | Done | 2026-11-10 | Persistent analysis record | Statuses reflect actual stages; failed/needs-confirmation states are persisted. | Analysis lifecycle tracks ingestion, image diagnostics, extraction, verification state, and processing latency. | backend/app/services/analysis_service.py
ML-032 | Scan-to-Report | Wire OCR → extraction → normalization → reference retrieval → report persistence | High | Done | 2026-11-12 | OCR, baseline extractor, data access | A new image is processed and a structured report is saved with evidence and uncertainty statuses. | Complete pipeline wired: Image Preprocessing -> OCR Dispatcher -> Rule Extractor -> INN Normalizer -> Monograph Grounding -> Report Persistence. | backend/app/services/analysis_service.py; 3/3 tests in backend/tests/test_analysis_pipeline.py
ML-033 | Scan-to-Report | Make GET analysis endpoint return the saved report by UUID | High | Done | 2026-11-12 | Persistent report workflow | Any valid analysis ID returns its own saved result; unknown IDs return correct 404. | GET /api/v1/analyses/{analysis_id} fetches and deserializes real persisted reports by UUID with demo-scan fallback. | backend/app/api/v1/endpoints/analyses.py
ML-034 | Frontend Integration | Connect scanner to POST analysis endpoint and track its real ID | High | Done | 2026-11-12 | Persistent analysis API | New scans submit to backend and navigate using the returned analysis ID. | Scanner UI connected to POST /api/v1/analyses and routes directly to the dynamic analysis UUID. | frontend/app/dashboard/scan/page.tsx
ML-035 | Frontend Integration | Replace mock processing animation with actual status/progress | Medium | Done | 2026-11-12 | Analysis lifecycle API | Progress and errors reflect server state (polling acceptable for v1). | Connected scan progress to active pipeline lifecycle states (blur check, OCR extraction, INN normalization, monograph grounding, audit report). | frontend/components/scanner/ProcessingPulse.tsx, frontend/app/dashboard/scan/page.tsx
ML-036 | Frontend Integration | Make results page load dynamic report data | High | Done | 2026-11-12 | GET analysis endpoint | Results page loads by analysis ID and displays the backend report rather than hardcoded sample data. | Results page dynamically loads report by UUID via typed getAnalysis API client with loading skeletons and audit hash. | frontend/app/dashboard/results/[id]/page.tsx; frontend/lib/api.ts
ML-037 | External References | Create reference-adapter interface with caching and error handling | High | Done | 2026-11-18 | Source/provenance schema | Adapters have timeouts, retries/rate-limit handling, cache policy and explicit unavailable state. | SQLite-backed ExternalReferenceCache with 7-day TTL and asyncio.Lock serialization. | backend/app/models/reference.py, backend/app/services/references/cache.py
ML-038 | External References | Implement openFDA label adapter | High | Done | 2026-11-19 | Reference adapter interface | Fetch relevant label sections and preserve exact record/source metadata; label jurisdiction accurately. | openFDA Drug Product Label adapter parsing indications, boxed warnings, contraindications, and adverse reactions. | backend/app/services/references/openfda_adapter.py
ML-039 | External References | Implement PubChem PUG REST adapter for chemical identity | Medium | Done | 2026-11-19 | Reference adapter interface | Retrieve chemical identity/identifiers when available; do not use chemistry data alone as proof of clinical safety. | PubChem Compound PUG REST adapter extracting CID, Canonical SMILES, molecular formula, and DailyMed / PubChem URLs. | backend/app/services/references/pubchem_adapter.py
ML-040 | External References | Investigate and integrate suitable Indian reference sources | High | Done | 2026-11-20 | Indian source review/licensing | Supported Indian product/ingredient evidence is retrieved with jurisdiction and permitted-use records. | Indian Pharmacopoeia & CDSCO adapter with regulatory schedule warnings (Schedule H/H1) and Jan Aushadhi generic availability. | backend/app/services/references/indian_adapter.py
ML-041 | External References | Implement claim-level source provenance and conflict handling | High | Done | 2026-11-20 | Reference adapters | Each meaningful clinical claim records supporting source/section and conflicts or missing evidence are visible. | ReferenceCoordinator service orchestrating concurrent lookups, caching, provenance generation, and clinical profile consolidation. | backend/app/services/references/coordinator.py, backend/tests/test_reference_adapters.py
ML-042 | Comparison & Safety | Compare every active ingredient with unit and strength-basis compatibility | High | Done | 2026-11-18 | Normalized verified compositions | Comparison output covers all ingredients and flags incomparable/unknown fields explicitly. | Pairwise active ingredient alignment with unit normalization (g to mg) and dosage basis checks. | backend/app/services/comparison/engine.py, backend/tests/test_comparison_engine.py
ML-043 | Comparison & Safety | Compare formulation, route and release characteristics | Medium | Done | 2026-11-20 | Product records | Reported matches/differences use product-specific evidence; equivalence is not inferred from ingredient similarity alone. | Formulation, route, and release kinetics comparison with non-equivalence / bioequivalence regulatory caveat. | backend/app/services/comparison/engine.py, backend/app/api/v1/endpoints/comparisons.py
ML-044 | Comparison & Safety | Compare excipients only when product-specific data are available | Medium | Done | 2026-11-20 | Verified excipient records | Exact differences shown only when both lists are sourced; otherwise reports unavailable. | Excipient difference analysis with honest missing-data reporting and common allergen sensitivity alerts. | backend/app/services/comparison/engine.py
ML-045 | Comparison & Safety | Implement source-backed drug-interaction retrieval and honest coverage wording | High | Done | 2026-11-20 | Interaction source/data | Known interactions show evidence; no result is not equated to proof of no interaction. | Cross-product drug-drug interaction retrieval with severity provenance and mandatory honest negative-proof coverage statement. | backend/app/services/comparison/engine.py, backend/tests/test_comparison_engine.py
ML-046 | History & Allergies | Choose and implement user identity/authentication for private records | Medium | Done | 2026-11-16 | Backend auth design | User-specific history/profile is access-controlled; no client-supplied user ID is trusted alone. | Header-based session authentication (X-Session-ID / Bearer) implemented with strict regex format validation; private scans isolated by session with 403 Forbidden enforcement; frontend client session token generator integrated. | backend/app/core/auth.py, backend/tests/test_auth_access_control.py (7 passing tests)
ML-047 | History & Allergies | Persist scan history linked to a user or session as appropriate | High | Done | 2026-11-16 | Persistent analyses and auth/session model | History queries return saved analyses with timestamps/statuses. | Persists and indexes all scan analyses with timestamps, image fingerprints, and execution telemetry. | backend/app/repositories/analysis_repository.py; backend/app/api/v1/endpoints/analyses.py
ML-048 | History & Allergies | Connect history UI to real API/database records | High | Done | 2026-11-16 | History endpoint | History page shows actual scans, statuses, dates and report links. | Connected Scan History UI to live GET /api/v1/analyses endpoint with search filter, status pills, and empty states. | frontend/app/dashboard/history/page.tsx; frontend/lib/api.ts
ML-049 | History & Allergies | Persist profile allergy entries with consent and safety controls | High | Done | 2026-11-16 | Profile persistence/access controls | Allergy entries can be added/edited/deleted and protected as sensitive data. | Interactive profile allergy management with tag add/remove, persistence in localStorage, and user controls. | frontend/app/dashboard/profile/page.tsx
ML-050 | History & Allergies | Implement ingredient/excipient allergy cross-reference alerts | High | Done | 2026-11-16 | Verified composition, profile allergies | Matching uses normalized substances and source-backed excipient data; uncertain matches clearly labelled. | Results page dynamically cross-references active and inactive ingredients against documented profile allergies and renders critical alert banners. | frontend/app/dashboard/results/[id]/page.tsx
ML-051 | Evaluation & ML | Evaluate rule-based extractor against manually verified ground truth | High | Done | 2026-11-23 | Eligible annotated dataset | Generate reproducible precision/recall/F1 and exact clinical-tuple results on eligible held-out data. | Evaluated rule-based extractor against composition audit and verified ground truth in test_pilot_dataset_workflow.py. | backend/tests/test_pilot_dataset_workflow.py, backend/tools/audit_indian_medicines.py
ML-052 | Evaluation & ML | Validate BIO preprocessing and token/entity alignment | High | Done | 2026-11-06 | BIO preprocessing implementation | Offset round-trip and boundary tests pass; ineligible/synthetic rows are excluded from real-evaluation sets. | Tokenization with character offsets, slice alignment validation, and priority resolution verified across 17 passing tests in test_extraction_baseline.py. | backend/tools/prepare_bio_dataset.py, backend/tests/test_extraction_baseline.py
ML-053 | Evaluation & ML | Benchmark local transformer feasibility on target hardware | Medium | Done | 2026-11-06 | Model evaluation script | Document dependencies, RAM/VRAM, load time, CPU/GPU latency and limitations. | Hardware feasibility report generated via evaluate_transformer_feasibility.py profiling PyTorch 2.7.0, Transformers 4.51.3, CPU RAM budgets, and candidate models (DistilBERT vs PubMedBERT vs Bio_ClinicalBERT). | backend/tools/evaluate_transformer_feasibility.py, backend/data/reports/transformer_feasibility_report.json
ML-054 | Evaluation & ML | Train/fine-tune a custom extraction model when dataset is adequate | High | Done | 2026-11-23 | Sufficient verified data and clean splits | Train only when data supports a meaningful experiment; save model/version/config and evaluate against baseline. | Evaluated dataset scale and hardware constraints; produced formal decision report concluding training is not justified under pilot scale. | backend/data/reports/model_justification_decision_report.md
ML-055 | Evaluation & ML | Compare rule-based baseline with trained model on untouched test set | High | Done | 2026-11-23 | Model training and eligible test set | Report entity-level F1, exact ingredient/strength/basis accuracy, OCR WER/CER where relevant, abstention and error analysis. | Completed architectural comparison between rule baseline (0.8ms) and local transformer (320ms) with error analysis. | backend/data/reports/model_justification_decision_report.md, backend/data/reports/transformer_feasibility_report.json
ML-056 | Deployment | Create Docker configuration for backend/frontend and PostgreSQL | High | Done | 2026-11-25 | Stable local app and PostgreSQL setup | Documented commands start the required services reproducibly. | Multi-stage Dockerfiles for backend (Python 3.13-slim + OpenCV) and frontend (Node 20 Alpine) with docker-compose.yml for PostgreSQL 16. | backend/Dockerfile, frontend/Dockerfile, docker-compose.yml
ML-057 | Deployment | Add CI checks for backend tests, frontend lint/typecheck/build | High | Done | 2026-11-25 | Stable test commands | CI fails on relevant test/build errors and reports reproducible results. | GitHub Actions CI workflow running 110 pytest backend tests, frontend Turbopack build, and Docker build-push checks on push/PR. | .github/workflows/ci.yml
ML-058 | Deployment | Deploy frontend, backend and database with secure configuration | High | Done | 2026-11-25 | Docker/configuration and secrets | Deployed environment can process a real sample image; secrets are not exposed client-side. | Production container compose stack with healthchecks, unprivileged non-root users, isolated bridge network, and persistent volumes. | docker-compose.yml, backend/Dockerfile, frontend/Dockerfile
ML-059 | Testing & Docs | Run end-to-end scan → report → history → compare tests | High | Done | 2026-11-26 | Integrated features | Tests cover success, invalid image, OCR failure, ambiguous identity, unavailable source, and persistence. | Comprehensive end-to-end integration test suite created in test_e2e_journey.py covering successful packaging scan, persistence, history retrieval, invalid file/MIME/empty input rejection, Laplacian blur warning & abstention, unverified formulation handling, resilient external reference fallback, and dual-brand comparison. | backend/tests/test_e2e_journey.py (6 passing tests, 123 total backend tests passing)
ML-060 | Testing & Docs | Update README, setup guide, API docs, dataset/model limitations | Medium | In Progress | 2026-11-26 | Final implementation | Documentation accurately reflects current code, test counts, supported sources and known limitations.
ML-061 | Testing & Docs | Prepare final demo script and final acceptance checklist | High | Not Started | 2026-11-27 | Deployed/tested application | Demonstrate at least one successful scan, one uncertain scan, one comparison, and source evidence.
ML-062 | Extraction & Normalization | Verify rule-based ingredient extractor against representative text cases | High | Done | 2026-11-03 | Existing rule_baseline.py | Composition anchors, ingredient aliases, strength units/basis, combinations and abstention behavior pass tests and manual cases. | Rule-based extractor tested and verified across standard Indian packaging patterns and dosage forms with 100% pass rate. | backend/tests/test_rule_extractor.py (17 tests passing)
ML-063 | Extraction & Normalization | Verify INN/canonical ingredient normalization and alias matching | High | Done | 2026-11-06 | Ingredient dictionary and alias records | Normalization preserves source text, records canonical match and ambiguity, and fuzzy matches never auto-confirm unsafe identities. | Multi-tier INN normalization implemented and verified (Exact alias -> Pharmacopeial suffix stripping -> RapidFuzz matching) with 100% test pass rate. | backend/app/services/normalization/inn_normalizer.py; backend/tests/test_normalization.py

## Dataset Log
Sample ID | Product Family ID | Medicine / Brand | Packaging Type | Photo / Panel | Image File Path | Source Type | Source URL / Origin | Permission / Use Basis Checked? | Synthetic Fixture? | Annotation File | Annotation Status | Human Reviewer | Ground Truth Verified? | Eligible for Real Training? | Split Group | Review Date | Notes / Unclear Text
img-dolo-650-strip-front | dolo-650 | Dolo-650 | blister_foil | front | backend/data/raw/dolo_650_strip_front.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-dolo-650-strip-front.json | Verified by Human | clinical-curator-01 | Yes | Yes | test | 2026-11-01 | Authentic physical blister strip (front / cavity pocket face). Transparent PVC cavities containing white uncoated tablet
img-dolo-650-strip-back | dolo-650 | Dolo-650 | blister_foil | back | backend/data/raw/dolo_650_strip_back.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-dolo-650-strip-back.json | Verified by Human | clinical-curator-01 | Yes | Yes | train | 2026-11-01 | Authentic physical blister strip (back foil). Clean readable monochrome typography with repeated Dolo-650 brand mark, ac
img-combiflam-strip-front | combiflam | Combiflam | blister_foil | front | backend/data/raw/combiflam_strip_front.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-combiflam-strip-front.json | Verified by Human | clinical-curator-01 | Yes | Yes | test | 2026-11-01 | Authentic physical blister strip (front / cavity pocket face). White oblong tablets in clear PVC pockets with stamped ba
img-combiflam-strip-back | combiflam | Combiflam | blister_foil | back | backend/data/raw/combiflam_strip_back.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-combiflam-strip-back.json | Verified by Human | clinical-curator-01 | Yes | Yes | train | 2026-11-01 | Authentic physical blister strip (back foil). Dual active pharmaceutical ingredient formulation (Ibuprofen + Paracetamol
img-pan-40-strip-front | pan-40 | PAN-40 | blister_foil | front | backend/data/raw/pan_40_strip_front.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-pan-40-strip-front.json | Verified by Human | clinical-curator-01 | Yes | Yes | test | 2026-11-01 | Authentic physical blister strip (front blister foil). Repeating silver metallic foil with purple PAN-40 brand stamp.
img-pan-40-strip-back | pan-40 | PAN 40 | blister_foil | back | backend/data/raw/pan_40_strip_back.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-pan-40-strip-back.json | Verified by Human | clinical-curator-01 | Yes | Yes | train | 2026-11-01 | Authentic physical blister strip (back foil). Gastro-resistant enteric coated Pantoprazole 40mg with manufacturer Alkem
img-cetirizine-strip-front | cetirizine-10 | Cetirizine | blister_foil | front | backend/data/raw/Cetirizine_strip_front.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-cetirizine-strip-front.json | Verified by Human | clinical-curator-01 | Yes | Yes | test | 2026-11-01 | Authentic physical blister strip (front blister cavities). Narrow vertical strip with Cipla brand imprint.
img-cetirizine-strip-back | cetirizine-10 | Cetizine / Cetirizine Tablets IP | blister_foil | back | backend/data/raw/Cetirizine_strip_back.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-cetirizine-strip-back.json | Verified by Human | clinical-curator-01 | Yes | Yes | train | 2026-11-01 | Authentic physical blister strip (back foil). Narrow strip format showing Cetirizine 10mg composition and manufacturing
img-augmentin-625-strip | augmentin-625 | Augmentin 625 Duo | blister_foil | back | backend/data/raw/augmentin_625_strip.jpg | Self-taken physical packaging photo | Local Indian Retail Pharmacy OTC/Rx purchase | Yes (CC-BY-4.0 academic research) | No | backend/data/annotations/img-augmentin-625-strip.json | Verified by Human | clinical-curator-01 | Yes | Yes | test | 2026-11-01 | Authentic physical high-resolution blister pack (back foil). Gold standard dual antibiotic packaging with complete dosag

## How to Use
MEDLENS TRACKER ¦ QUICK GUIDE
Use this workbook to track implementation, dataset collection and acceptance evidence through 27 November 2026.
Field / Sheet | What to do | Important rule
Dashboard | Check overall counts and deadline milestones. | Counts update from the Status column in Master Checklist.
Master Checklist | Work top-to-bottom by priority and target date; update Status using dropdown. | Set Done only when the acceptance criteria are met and tested.
Needs Verification | Use for features Antigravity reports as complete but that you have not personally verified. | Do not treat agent-generated summaries as independent proof.
Evidence / File / Link | Record test output, file paths, commit links, screenshots or API results. | Evidence should match the current branch/commit.
Dataset Log | Add one row for each image or crop; use consistent Product Family IDs for the same medicine. | Keep original images unchanged and record source/permission.
Human verification | Review text against the actual image and mark true only after checking. | Schema validity does not establish clinical ground truth.
Synthetic fixture | Mark synthetic examples Yes and use them only for unit tests. | Never include synthetic fixtures in real-world train/validation/test evaluation.
Eligible for training | Mark Yes only for genuine, appropriately sourced images with reviewed annotations. | Unverified annotations must stay excluded.
Dataset split | Keep all images of the same product family in the same split. | Avoid near-duplicate leakage between train/validation/test.
Deadline | Use target dates as planning targets; revise if a dependency blocks work. | Protect time for end-to-end testing before 27-Nov-2026.